## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | OJ_Registration001
Project Name | Online Journey
Prepared/Modified by | Role | Date of Preparation
Shubham Nigam | Tester | 2018-09-22
Reviewed by | Role | Date of Review
Harish | SME
Approved by | Role | Date of Approval
Test Manager
Circulation List
Version Number | 1

## DEFECT TRACKING SHEET
Project ID: PROJECT_001 |  | Project Name : Online Journey
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_SIGNUP_001 | SIGNUP | SignUp is not available, So the user is not able to signup. | Detailed Description: The website doesnot have signup page. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. There is not signUp page link available on the website Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application does not have SignUp page.The application Display Username available.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_001
DF_SIGNUP_002 | Update Hotel | After filling all the valid inputs, data is not being updated in database. | Detailed Description: UpdateHotel Button is not working. After filling all the valid inputs, data is not being updated in database. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter valid userid 4. Enter valid password 5. Login as admin 6.Click on update hote link 7. Enter valid Hotel city 8. Enter valid Hotel Name 9. Enter valid Description 10. Enter valid Average Fare Per Night 11.Enter valid phone number1 12. Enter valid phone number2 13 Select rating 14.Enter valid Email 15.Enter valid fax 16.Click on UpdateHotel Button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application does not update the corresponding details in database.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_002
DF_SIGNUP_003 | Update Hotel | It is accepting phone number more than 10 digit.After filling all the valid inputs with phonenumber1 as invalid (more than 10 digit). | Detailed Description: UpdateHotel Button is not working. After filling all the valid inputs, data is not being updated in database. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter valid userid 4. Enter valid password 5. Login as admin 6. Click on update hote link 7. Enter valid Hotel city 8. Enter valid Hotel Name 9. Enter valid Description 10.Enter valid Average Fare Per Night 11.Enter invalid phone number1 12.Enter valid phone number2 13.Select rating 14.Enter valid Email 15.Enter valid fax 16.Click on UpdateHotel Button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application does not update the corresponding details in database.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_002
DF_SIGNUP_004 | Update Hotel | It is accepting invalid email id .After filling all the valid inputs with email as invalid (without @ symbol). | Detailed Description: It is accepting invalid email id .After filling all the valid inputs with email as invalid (without @ symbol) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter valid userid 4. Enter valid password 5. Login as admin 6. Click on update hote link 7. Enter valid Hotel city 8. Enter valid Hotel Name 9. Enter valid Description 10.Enter valid Average Fare Per Night 11.Enter valid phone number1 12.Enter valid phone number2 13.Select rating 14.Enter invalid Email 15.Enter valid fax 16.Click on UpdateHotel Button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the wrong formatted email id.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_002
DF_SIGNUP_005 | Update Hotel | It is accepting invalid Averaage fare per night(accepting string) .After filling all the valid inputs with invalid Averaage fare per night . | Detailed Description: It is accepting invalid email id .After filling all the valid inputs with email as invalid (without @ symbol) Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter valid userid 4. Enter valid password 5. Login as admin 6. Click on update hote link 7. Enter valid Hotel city 8. Enter valid Hotel Name 9. Enter valid Description 10.Enter invalid Average Fare Per Night 11.Enter valid phone number1 12.Enter valid phone number2 13.Select rating 14.Enter invalid Email 15.Enter valid fax 16.Click on UpdateHotel Button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts the wrong formatted email id.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_002
DF_LOGIN_001 | Login | It is not showing error message while wrong username and wrong password is provided by user | Detailed Description: It is not showing error message while wrong username and wrong password is provided by use. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter invalid userid 4. Enter invalid password 5. Select as admin 6. Click on login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application doesnot respond when wrong userid and wrong password is provided.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_002
DF_LOGIN_002 | Login | It is not showing error message while valid username and wrong password is provided by user | Detailed Description: It is not showing error message while valid username and wrong password is provided by user Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter valid userid 4. Enter invalid password 5. Select as admin 6. Click on login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application doesnot respond when valid userid and wrong password is provided.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_002
DF_LOGIN_003 | Login | It is not showing error message while invalid username and valid password is provided by user | Detailed Description: It is not showing error message while invalid username and valid password is provided by user Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter invalid userid 4. Enter valid password 5. Select as admin 6. Click on login button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application doesnot respond when valid userid and wrong password is provided.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_002
DF_LOGIN_004 | Login | login for user not found in login page | Detailed Description: login for user not found in login page Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Enter invalid userid 4. Enter invalid password 5. Click on select to login as user Actual result observed on running above steps: login for user not found in login page.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_002
DF_LOGIN_005 | Login | It is not showing error message while username and password field are left blank | Detailed Description: It is not showing error message while username and password field are left blank 1. Open Browser 2. Enter URL for the website 3. userid left blank 4. password left blank 5. Select as admin 6. Click on login button Actual result observed on running above steps: It is not showing error message while username and password field are left blank.There is no Alert message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-09-22 | Shubham Nigam |  |  | Test Cycle 1 | TC_Reg_002
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.